## Gantt Chart
TEAM 3 GANTT CHART
Client: | PUP Sta. Rosa Branch |  | Project Manager | Joshua Arceo
Title of Project: | PUP Sta. Rosa Campus Student Organization Automated Election System |  | Business Analysts | Tristan Pecayo
Duration of Project: | 4 Months |  |  | Donna Mendiola
Project Starting Date: | 2024-03-07 |  | Quality Assurance | Wayne Calago
Chorlyn Dimaculangan
|  |  | Developer | Ivan Bandilla
| Start Date | End Date | Progress | Task Status |  |  |  |  | MARCH
Workload/Task |  |  |  |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Identify Goals | 2024-03-08 | 2024-03-11 | 100% | Completed | bar: 8 to MARCH 11
Identify Roles | 2024-03-07 | 2024-03-10 | 100% | Completed | bar: 7 to 10
Identify Deliverables | 2024-03-07 | ---- | 10% | In Progress | bar: 7 to MARCH 13
Survey using Gforms | 2024-03-08 | 2024-03-10 | 100% | Completed | bar: 8 to 10
Creation of Road Map | 2024-03-07 | ---- | 25% | In Progress | bar: 7 to 8
Creaation of Sprint Goals for the Month | 2024-03-07 | ---- | 25% | In Progress | bar: 7
Create Gantt Chart | 2024-03-07 | ---- | 15% | In Progress | bar: 7
Business Process Flow | 2024-03-08 | 2024-03-10 | 100% | Completed | bar: 7
Needs Assesments | 2024-03-09 | 2024-03-10 | 100% | Completed | bar: 9 to 10
Follow Up Question for President of (PIIE) | 2024-03-10 | 2024-03-11 | 100% | Completed | bar: 10 to MARCH 11

## Sheet3
Choose Task Status
In Progress
Pending
Completed
Delayed